# Growth Plan: 500 Final-Year Registrations in 7 Days

Workshop: “Build Your First AI Project in 60 Minutes” · Budget: ₹2,000 · Author: Sinchana Shetty

## 1. Who I’m targeting

Primary persona: “Placement-anxious Priya/Ravi”: a final-year engineering student (CSE/IT/AIML first, ECE/EEE second) at a tier-2 or tier-3 college, in the middle of campus placement season.

| What they feel | “Everyone says AI, I have no project to show. I’m late.” |
| --- | --- |
| What they’ve tried | YouTube playlists, half-finished courses, copy-paste mini-projects |
| Biggest fear | Being asked “what have you built?” in an interview and having nothing real |
| Where they live | College WhatsApp groups, club/department groups, Instagram, LinkedIn, Telegram |
| Who they trust | Classmates and seniors, not ads |

Why they’d care: a project is the one thing that moves interview outcomes, and this promises one in an hour, for free.

What makes them register (4 triggers): 1. Concrete outcome: “leave with a working project + GitHub link + a resume line”, not “learn AI”. 2. Low risk: free, 60 minutes, no experience needed. 3. Personal relevance: the project picker shows their branch and their topic. 4. Friends: a friend sent it and a friend is going.

## 2. Campaign: 4 channels, no more

Insight: this audience registers when a peer sends it in a group they already read. So paid ads get the smallest share of budget and peer distribution gets most of the effort.

| # | Channel | What I do | Why it works | Regs |
| --- | --- | --- | --- | --- |
| 1 | WhatsApp via campus ambassadors | Recruit 30 final-years (class reps, club leads) via LinkedIn/Instagram DMs. Give each a ready message, poster and a personal tracked link. They post in ~3 groups each. | Trusted sender, group the student already reads, zero cost | 170 |
| 2 | Email to clubs, TPOs and HODs | AI-personalised email to 200 coding/AI/IEEE clubs and placement cells using public contact pages. Ask for one forward to their student group. Two waves (Day 2, Day 5). | Faculty/club forwards carry authority; ~20% respond | 90 |
| 3 | Referral loop (built into landing page) | Every registrant gets a personal link + share card. Unlocks: 1 friend = Starter Kit, 3 = Interview Cheat-Sheet, 5 = priority Q&A, top 5 = ₹100 voucher. | Turns each signup into a distributor; the tiers reward small effort | 110 |
| 4 | Social media (Instagram Reels, YouTube Shorts, WhatsApp Status, LinkedIn) | 5 short reels (finished project demo, “pick your project”, rewards reveal, before/after resume) made with the Poster Studio + a content pack; ambassadors and campus pages repost; boost the best reel with ₹1,000. | Where students already scroll; reels show the outcome and the rewards in 15 seconds | 130 |
|  |  |  | Total | 500 |

### 7-day calendar

| Day | Focus |
| --- | --- |
| 1 | Finish page, tracker, posters. Recruit ambassadors. Seed 20 registrations from friends/network. Story teaser. |
| 2 | Ambassadors go live. Email wave 1. Reel 1 + LinkedIn post. |
| 3 | Nudge #1 in groups. Share first leaderboard. Check dashboard: which source leads? |
| 4 | Reel 2; boost the best performer at ₹1,000. Telegram groups. |
| 5 | Email wave 2. Reel 3 (rewards). Referral push to existing registrants. |
| 6 | Reel 4. DMs to ambassadors who are behind. “Last 48 hours” status. |
| 7 | Reel 5, final call, reminder with joining link to all registrants. |

### Math (so 500 is not a wish)

- 500 registrations ÷ ~30% visit-to-register (warm, peer-sent traffic) ≈ 1,650 visits needed.

- Ambassadors: 30 × 3 groups × ~60 members ≈ 5,400 views → ~3% register ≈ 170.

- Emails: 200 sent → ~28 forwards × ~80-member groups → ≈ 90.

- Referrals: ~30% of the first ~390 share and bring ~1 each ≈ 110.

- Social: ~15,000 organic views × ~0.5% register ≈ 75, plus the ₹1,000 boost (~140 clicks at ~₹7, ~35% register ≈ 50) ≈ 125–130. These are estimates; reach varies a lot.

- If a channel runs 30% short, the dashboard shows it by Day 3 and I move effort to the best performer.

### Budget: ₹2,000

| Item | ₹ |
| --- | --- |
| Top-5 referral vouchers (₹100 each) | 500 |
| Boost the best-performing reel (Day 4–5) | 1,000 |
| Buffer (domain / tools / replacement vouchers) | 500 |

Everything else is free: AI for copy and personalisation, Canva free, GitHub Pages for hosting.

### How I’ll know it’s working (checked daily in the dashboard)

Registrations per day, source mix, referral share, projected finish. Target by end of Day 3: 150+. If below 100, I cut the weakest channel and re-push the strongest.

## 3. What I built

A landing page + referral engine + control-room dashboard (see /landing). Highlights: a lab-themed “Builder ID” sign-up where each student gets a codename and class, personal referral link, ranks that unlock rewards (Recruit → Pioneer), downloadable share card, branch-specific project picker, live seat meter and leaderboard, and a dashboard that tracks channel performance and projects whether 500 will be hit. Plus a Poster & Caption Studio (/social) that makes post/story/LinkedIn graphics with the rewards strip, and per-platform captions with tracked links.